## Sheet1
Day | Task name | What the task entails | 1 | Actual hours
17.08.2021 | Team meeting | Discussed about mechanics we'd like to implement to make our prototype unique from other games in the souls-like genre. | 1 | 3
18.08.2021 | Arena concept | Tried 3D concepting by modelling a dais and some half wall variants. Decided to stick with 2D. Went for a gothic cathedral-esque look for the exterior. The interior is based off a design I found from Guild Wars 2. | 2 | 1.88
18.08.2021 | Arena blockout in unity | Made a quick blockout using 3D models I made earlier along with probuilder ones. | 0.5 | 0.28
20.08.2021 | Team meeting | Discussed what we've done over the past couple of days and what we plan to implement before we show the prototype to the lecturers next week. | 1 | 0.55
22.08.2021 | Moodboard collection | Gathered references of props needed along with exterior and interior references of Gothic architecture. | 1 | 0.73
22.08.2021 | Candlestick | Modelled a 2k poly candlestick to be used as a semi-placeholder for the arena. | 1 | 0.52
22.08.2021 | Pew | Modelled a 400 poly pew to be used as a semi-placeholder for the arena. | 1 | 0.81
22.08.2021 | Altar placeholder | Made rectangular model as a placeholder | 0.1 | 0.1
22.08.2021 | Implement new props in scene | Put new props. Had to scale them down to the player. Adjusted scale of the arena and props to match the current player height. | 0.5 | 0.46
22.08.2021 | Fiddle with lighting | Changed skybox, added point light to candles. I tried to make the lighting nicer with some lightmaps but almost cooked my CPU while doing so. Decided to leave the heavier 3D workloads to my teammates with more competent workstations. | 1 | 0.63
22.08.2021 | Tried making modular balcony set | Pulled up my reference board and tried to make a modular balcony set. Gave up after making several variations that didn't look good. | 1 | 1.24
22.08.2021 | Made a modular wall piece | Pulled up my reference board and made a modular wall. Unpacked the UVs as well. | 1 | 0.88
Total |  |  | 11.1 | 11.08