## Sheet1
Day | Task name | What the task entails | 1 | Actual hours
17.08.2021 | Team meeting | Discussed about mechanics we'd like to implement to make our prototype unique from other games in the souls-like genre. | 1 | 3
18.08.2021 | Arena concept | Tried 3D concepting by modelling a dais and some half wall variants. Decided to stick with 2D. Went for a gothic cathedral-esque look for the exterior. The interior is based off a design I found from Guild Wars 2. | 2 | 1.88
18.08.2021 | Arena blockout in unity | Made a quick blockout using 3D models I made earlier along with probuilder ones. | 0.5 | 0.28
20.08.2021 | Team meeting | Discussed what we've done over the past couple of days and what we plan to implement before we show the prototype to the lecturers next week. | 1 | 0.55
22.08.2021 | Moodboard collection | Gathered references of props needed along with exterior and interior references of Gothic architecture. | 1 | 0.73
22.08.2021 | Candlestick | Modelled a 2k poly candlestick to be used as a semi-placeholder for the arena. | 1 | 0.52
22.08.2021 | Pew | Modelled a 400 poly pew to be used as a semi-placeholder for the arena. | 1 | 0.47
22.08.2021 | Altar placeholder | Made rectangular model as a placeholder, implemented and adjusted scale in Unity scene. | 0.1 | 0.1
22.08.2021 | Implement new props in scene | Put new props. Had to scale them down to the player. Adjusted scale of the arena and props to match the current player height. | 0.5 | 0.46
22.08.2021 | Fiddle with lighting | Changed skybox, added point light to candles. I tried to make the lighting nicer with some lightmaps but almost cooked my CPU while doing so. Decided to leave the heavier 3D workloads to my teammates with more competent workstations. | 1 | 0.63
22.08.2021 | Tried making modular balcony set | Pulled up my reference board and tried to make a modular balcony set. Gave up after making several variations that didn't look good. | 1 | 1.24
22.08.2021 | Made a modular wall piece | Pulled up my reference board and made a modular wall. Unpacked the UVs as well. | 1 | 0.88
23.08.2021 | Skybox | Made a night skybox, decided to cut the moon since the player camera is unable to tilt to the degree where the moon would be visible. | 1 | 0.94
23.08.2021 | Found fonts | Found fonts, put their ttf files in the font folder. Also made a txt file explaining their usages and how well they look when used for numbers or large blocks of text. | 0.1 | 0.31
23.08.2021 | Team meeting | Had a meeting where we discussed what we've done, and what we need to finish ASAP for tomorrow's feedback session. | 1 | 0.59
23.08.2021 | Boss HP Bar | Made boss HP bar and implemented it into the HUDManager in Unity. | 0.5 | 0.43
23.08.2021 | Player Health and Stamina Bar | Made player HP and stamina bar and implemented it into the HUDManager in Unity. | 0.5 | 0.6
23.08.2021 | Unwrapped candlestick model | Started unwrapping the candlestick model. Realised there was an error within the mesh, so I had to fix it. Then I resumed unwrapping. | 1 | 1.77
23.08.2021 | Started progress on altar model | Added more detail into the altar prop. | 1 | 0.73
24.08.2021 | Unwrapped pew model | Unwrapped the church pew model. | 0.5 | 0.82
24.08.2021 | Unwrapped the altar model | Unwrapped the altar model. | 1 | 1.25
25.08.2021 | Start screen implement | Copied Roger's current scene to make a 3D start screen. Searched for fonts (since they weren't really suitable). We also decided on the official name of the game, Gallant. Made a press A to start sprite that'll show in the bottom. | 1 | 0.73
25.08.2021 | Adrenaline UI | Made adrenaline UI using a similar process for the other resource bars, where the background, fill, specular and border layers are separated. Implemented these pngs into the HUDManager. | 1 | 0.89
25.08.2021 | Rearranged ingame UI | Rearranged resource bars to make the UI look visually pleasing. | 0.5 | 0.52
25.08.2021 | Fixed UV map on pew model | Edited the UV map for the pew model. | 0.1 | 0.1
25.08.2021 | Filled in individual journal and development journal | Wrote entries on the contributions I've done so far. Proofread and corrected contributions written by other teammates. | 1 | 1.5
27.08.2021 | Tweaked start screen | Tweaked start screen title placement and size. Also updated 3D backdrop with Roger's new scene. | 0.1 | 0.17
27.08.2021 | Custom Title | Made a custom title based off Fenrir Regular. | 0.1 | 0.28
27.08.2021 | Custom Application Icon | Made from rotating the T from the custom title. | 0.1 | 0.06
Total |  |  | 21.6 | 22.43