## Sheet1
Day | Task name | What the task entails | 1 | Actual hours
17.08.2021 | Team meeting | Discussed about mechanics we'd like to implement to make our prototype unique from other games in the souls-like genre. | 1 | 3
18.08.2021 | Arena concept | Tried 3D concepting by modelling a dais and some half wall variants. Decided to stick with 2D. Went for a gothic cathedral-esque look for the exterior. The interior is based off a design I found from Guild Wars 2. | 2 | 1.88
18.08.2021 | Arena blockout in unity | Made a quick blockout using 3D models I made earlier along with probuilder ones. | 0.5 | 0.28
20.08.2021 | Team meeting | Discussed what we've done over the past couple of days and what we plan to implement before we show the prototype to the lecturers next week. | 1 | 0.55
22.08.2021 | Moodboard collection | Gathered references of props needed along with exterior and interior references of Gothic architecture. | 1 | 0.73
22.08.2021 | Candlestick | Modelled a 2k poly candlestick to be used as a semi-placeholder for the arena. | 1 | 0.52
22.08.2021 | Pew | Modelled a 400 poly pew to be used as a semi-placeholder for the arena. | 1 | 0.81
Total |  |  | 7.5 | 7.77